## PCR Register Template
Physical climate risk register template
This template should be used alongside Resilient Infrastructure: Physical climate risk assessments for defensible decision-making.
Developed by Timothy Grech, QIC Infrastructure and Dr Kate Simmonds, IGCC.
Note: adaptation planning is not covered in detail in Resilient Infrastructure: Physical climate risk asssessments for defensible decision-making but may be covered in future work.
Develop understanding of risk | [11 empty] | Detailed risk assessment | [14 empty] | Adaptation Planning
[13 empty] | Scenario 1 - SSP2-4.5 | [5 empty] | Scenario 2 - SSP3-7.0 / SSP5-8.5 | [7 empty] | Planned Adaptation | [9 empty] | Implemented Adaptation
Risk ID | Risk Narrative | Risk Type | Location | Impacted Asset Type/Component | [5 empty] | Impact Type | Asset Life Span / Time Horizon | Existing Controls | Likelihood Rating | Likelihood Justification | Consequence Rating | Consequence Category | Consequence Justification | Initial Risk Rating | Likelihood Rating | Likelihood Justification | Consequence Rating | Consequence Category | Consequence Justification | Initial Risk Rating | Level of Confidence (LoC) | LoC Comment | Adaptation Measures Needed | Adaptation Measures | Scenario Modelled | Scenario Comment | Likelihood Rating | Likelihood Justification | Consequence Rating | Consequence Category | Consequence Justification | Residual Risk Rating | Implemented Adaptation Measure | Actual Residual Risk Rating
|  |  |  | Turbine | Solar PV | Substation | Transmission | Access | People
[ Note: Unique Identifier] | [ Note: Risk narrative describing the hazard or climate variable, how the asset component is impacted, and the outcome ] [ Note: Location and specific asset agnostic in preliminary assessments (Steps 1-2), location and asset specific in final assessment (Step 3)] | [ Note: Distinguish between direct and interdependent risks] | [ Note: Distinguish between portfolio generally (preliminary assessment, Steps 1-2) and site location (Step 3) ] | [ Note: Categorise the asset component impacted by the risk narrative. There may be multiple risks per component and hazard.] [ Note: this can be used for interdependent risks where the indirect risk is linked back to an asset component, else n/a ] | [5 empty] | [ Note: Impact type (e.g., damage, disruption)] | [ Note: Asset Life Span informs the useful time horizon to assess the risk, and should inform the time horizons for climate projections. ] [ Note: For people related risks, this should be taken at the project life ] | [ Note: List the existing controls. This can include standard design measures and operational controls.] | [ Note: Rating from adopted risk matrix or where otherwise informed by SME.] | [ Note: The likelihood and resulting probability range should be justified.] | [ Note: Rating from adopted risk matrix.] | [ Note: Category from adopted risk matrix.] | [ Note: The method for informing consequence should by justified and supporting information linked. Could include asset sensitivity modelling or objective qualitative criteria analysis .] | [ Note: Resulting initial risk rating from adopted risk matrix ] | [ Note: Rating from adopted risk matrix ] | [ Note: The likelihood and resulting probability range should be justified.] | [ Note: Rating from adopted risk matrix ] | [ Note: Category from adopted risk matrix.] | [ Note: The method for informing consequence should by justified and supporting information linked. Could include asset sensitivity modelling or objective qualitative criteria analysis .] | [ Note: Resulting initial risk rating from adopted risk matrix ] | [ Note: LoC for initial risk ratings (see Step 6 for more information).] [ Note: Can be duplicated for emission scenario if useful (i.e., if different scenarios have different LoC)] | [ Note: Explain LoC column ] | [ Position on whether adaptation measure needed. Include justification if not needed (i.e., either negligible risk or outside of ability to influence) ] | [ Note: Description of adaptation measures, including the impact on consequence ] | [ Note: Justify the emission scenario adopted for calculating the residual risk, alternatively this can be duplicated for each but only one scenario can inform Actual Residual risk.] | [ Note: Justification of Scenario Modelled Column ] | [ Note: Liklihood with adaptation measures applied ] | [ Note: Justification of Likelihood Rating Column ] | [ Note: Consequence with adaptation measures applied, adaptation measures should change consequence ] | [ Note: Category from adopted risk matrix, this should be consistent with Column X] | [ Note: Justification of Conseuqence Rating Column ] | [ Note: Adjusted risk rating if adaptation measures are applied ] | [ Note: Confirm adaptation measures actually implemented, once relevant approval and funding processes are complete and measures are delivered. ] | [ Note: Actual Residual Risk Rating, once updated this should reflect the current state of the asset described] [ Note: Further implementation details can be added as needed ]
1 | Increased rainfall intensity and drier weather [link to climate variables ] cause flash flooding [resulting natural hazard ] which inundates substations [asset component and outcome] [Note: this can be further detail relative to site, and specific substation # where different from general risk.] | Direct | General | No | No | Yes | No | No | No | Damage to Asset | 75 - 100 | > Floor level is 100mm from ground level (concrete slab) | Possible (3) | [ Note: Base on AEP% where possible and align with risk matrix] Different AEP will result in different likelihood & consequence - SME decision on most useful. May be based on design standard (where uplift is then added for climate change) or another test event. | Minor (2) | Infrastructure Service | Informed by established and Melbourne Water endorsed flood model. Modelling run with 1% AEP including climate change uplift for RCP4.5 @ 2100 - 15.% uplift . Minor inundation above floor level. | High | Possible (3) |  | Major (4) | Infrastructure Service | Informed by established and Melbourne Water endorsed flood model. Modelling run with 1% AEP including climate change uplift for RCP8.5 @ 2100 - 18.5% uplift. Marked inundation above flood level, components compromised. | High | High | Flood modelling is an established method of informing sensitivity of asset to flood. | Yes | Raise flood level of substations impacted by 2100 / RCP8.5 event [ Risk would be parted out for individual substations requiring different adaptation ] | Scenario 2 -SSP5-8.5 | Asset is critical to operation, more conservative case adopted. | Possible (3) |  | Negligible (1) | Infrastructure Service | All impacted substations raised above 1% AEP at 2100. [ Note there is still a risk of inundation for more rare events. This can be covered in separate risk but the rating will be lower so may not justify adaptation.] | Low | Implemented in delivery of new substation X - built on XXXXX | Low
. | . | . | . | . | . | . | . | . | . | . | . | . | . | . | . | . | . | . | . | . | . | . | . | . | . | . |  | . | . | . | . | . | . | . | . | . | . | .

## Lists
Yes No | Location | Impact Type | Risk Type | Lifespan | Likelihood Rating | Consequence Rating | Consequence Category | LoC | Risk Rating | Scenario Modelled
Yes | General | Damage to Asset | Direct | 0 - 10 | Rare (1) | Negligible (1) | Infrastructure Service | Low | Low | Scenario 1 - SSP2-4.5
No | <Location 1> | Revenue Loss | Interdependent | 10 - 30 | Unlikely (2) | Minor (2) | Social | Medium | Moderate | Scenario 2 -SSP5-8.5
| <Location 2> | <insert> |  | 30 - 50 | Possible (3) | Moderate (3) | Governance | High | High
|  |  |  | 50 - 75 | Likely (4) | Major (4) | Financial |  | Extreme
|  |  |  | 75 - 100 | Almost Certain (5) | Catastrophic (5) | Environmental
Economic
<Location 10>